## Daily Status Tracker
Code Review using Copilot- Daily Status Tracker
Project Duration: 25.09.2025 to 12.10.2025 ¦ Total Hours: 80
Date | Day | Vishnu Priya P (TL) | Gokul Siddarth S | Kumpatla Sai Chaitanya | Dheeraj Sai Tiwari | SME Updates - Archana | SME Updates - Swapna
25.09.2025 | Thursday | Explored Blueverse Platform for better tool exposure. Coordinated with Group to discuss approach & workflow. Maintained Daily Status Tracker in Excel. Status Call with TLs & Ravi Sir to update project progress (10.30-11 AM IST) Discussion with SMEs & Ravi Sir on project implementation (7:30–8:00 PM IST). Project Use Case to be shared tomorrow. | Explored Blueverse Platform's resources and tutorial videos. Coordinated with group about the workflow. Discussion with SMEs and Ravi Sir. Explored about the m365 Copilot. | Explored Blueverse platform to assess project environment requirements. Collaborated with teammates to get clear understanding of the project title. Participated in a meeting with SMEs to gather insights and guidance. | Explored the Blueverse platform, engaged in discussions with teammates and subject matter experts (SMEs), and shared key takeaways and notes from the meeting of minutes. | Explored Blueverse Platform resource videos for better understanding of the platform. Project use case will be decided tomorrow. Prepared to share meeting status call update tomorrow. | Explored Blueverse Platform resource videos for better understanding of the platform. Project use case will be decided tomorrow. Prepared to share meeting status call update tomorrow based on feasible time.
26.09.2025 | Friday | Project Change: Due to Knowledge Fabric constraint in BlueVerse, SMEs plan to shift to Code Review using Copilot Check Permissions: Install Visual Studio 2022 GitHub Copilot license (check free version availability) Standup call with Ravi from (5.45 PM - 6.50 PM)- For Project status updates and blocker solving. Daily Status update: (9.30 PM - 10.10PM) - Project discussion and requirement details. Schedule Calls: With SMEs for next discussion. Maintain: Daily Status Tracker (Excel) Teams channel folders update with current files/resources Pending: Action Plan & Requirement Doc from SMEs. Understand problem statement in detail. | Discussion on project with team members. Initiated research on coding security standards for the "Code Review using Copilot" project. Explore GitHub Copilot's capabilities in code review. | Engaged in project discussion with teammates and meeting with SMEs. Initiated research on coding security standards for the "Code Review using Copilot" project. | Collaborated with teammates on project discussions and participated in brainstorming sessions with subject matter experts (SMEs). Initiated research on secure coding standards for the 'Code Review using Copilot' initiative. Explored GitHub Copilot’s capabilities and documented key insights and action items from the meetings. | Due to Knowledge Fabric constraint in BlueVerse, plan to shift to Code Review using Copilot. Checking access, permission, and license availability for visual studion 2022, copilot license. Also check if working in personal, college or LTI mail id. Requirement document shared soon. | Due to Knowledge Fabric constraint in BlueVerse, plan to shift to Code Review using Copilot. Checking access, permission, and license availability for visual studion 2022, copilot license. Also check if working in personal, college or LTI mail id. Requirement document shared soon.
27.09.2025 | Saturday | Weekend | Weekend | Weekend | Weekend | Weekend | Weekend
28.09.2025 | Sunday | Weekend | Weekend | Weekend | Weekend | Weekend | Weekend
29.09.2025 | Monday | SME Call: Rescheduled from 6:30–6:45 PM to 10:15–10:30 PM. Pending Items: Ticket Approval and License for Visual Studio 2022 and Azure SRE Agent – awaiting approval from Rathnavelu Sir. Requirement Documents – yet to be received. Completed: Attended Workshop: Campus to Corporate. Planned for Tomorrow: Start Web Development (Backend) project for Inventory Management. | Participated in the 'Campus to Corporate' workshop. Planned to begin backend development for the Inventory Management project tomorrow, following a team discussion on project goals and implementation strategy. | Attended 'Campus to Corporate' workshop till 4:30 pm. Reviewed and explored coding standards for AngularJS (frontend) and Node.js (backend) to ensure alignment with best practices. Initiated designing of the web application for the Code Review project. Waiting completion of Visual Studio 2022 installation to proceed further with implementation. | Attended the 'Campus to Corporate' workshop. For tomorrow, planned to initiate the backend development of the Inventory Management project. Also discussed project scope and approach with the team. | Gave idea about project workflow. Asked us to start with basic Inventory system web application. | No inputs, not joined the call.
30.09.2025 | Tuesday | Stand-up Call with Ravi Sir (12:30 PM – 1:15 PM) Reviewed overall project status. Takeaway: Expedite Visual Studio 2022 installation and close the pending ticket. Seek support from Ravi Sir and Rathnavelu Sir to push approvals forward. Escalation Spoke to Rathnavelu to coordinate with SCC team for pending approval. Daily Status Call with SMEs (6:30 PM – 6:50 PM) Did not Receive requirement document yet. Frontend updates on inventory features by individual team members. Initiate backend development using .NET, JavaScript, or Python. Use SQL or similar tools for database storage. GitHub Copilot Fine-Tuning Adopt single-instruction prompts for better accuracy. Maintain an Excel log of all instructions for future reference. Azure DevOps Dashboard Created dashboard for project management. Assigned tasks to team members. Tracking individual daily progress in Excel. | Worked on an inventory management app, where users can login and select their role as buyer or seller and here the buyer can view the dashboard of available products and the seller can sell their products with specific details. Now we were advised to enhance this app using github copilot as part of our project and document it. Also our SME's asked us to intiate a backend for this project. | Worked on basic inventory management application development. Collaborated with team to design the workflow. Had discussion with teammates and SMEs; shared key takeaways. | Worked on fine-tuning GitHub Copilot instructions and experimented with various prompts and their outcomes using Agent Mode. Currently focused on backend development for the Inventory Management project | Use Copilot to generate code skeletons, add functionality, and optimize code. Record effective prompts in Excel with their purpose. Use Copilot’s /optimize feature to improve performance and fix decoding errors. Perform code review, write specifications, and test code quality using Copilot. Start backend API development after Visual Studio 2022 license approval. Maintain a single codebase; use feature branches for individual testing. Session on knowledge fabric from Srinivas R in future. | SME Review/Input
01.10.2025 | Wednesday | Call with Ravi: No enterprise/commercial tools for non-billable employees; use non-commercial/educational versions of Visual Studio & Azure. Ticket & project status update shared between 12:30–12:45 PM. Escalation mail looped to Ravi, Rathinavelu, and SMEs regarding tool installation delay. Explored Azure services using college ID; accessed Cosmos DB and SRE agent (preview). Re-raised tickets for free version installation; coordinating with team on progress and blockers. Team call (3:30–4:00 PM): Discussed challenges, resolved a few, and shared status updates. Updated individual task progress in Azure Boards. | Worked on the developement of the inventory management app. Collaborated with Chaitanya to update the workflow and resovle errors. Added additional features to the app to make it more usable. Engaged in team discussions and meet with SMEs to clarify their requirements to work on it more. | Worked on the development of the Inventory management application. Collaborated with Gokul to update the workflow and resolve errors. Participated in discussions with teammates and the SME to clarify requirements and align on next steps.. | Contributed to backend development of an inventory management application. Collaborated closely with Vishnu Priya and actively participated in team discussions. Engaged with subject matter experts (SMEs) to clarify requirements and ensure accurate implementation. | Team instructed to raise individual tickets for free version installation. UI prototype ready; image integration and navigation fixes in progress. Prompt engineering repository initiated; team testing prompt variations and logging model outputs. Microsoft training resources on prompt engineering shared with team. Backend development on hold until Visual Studio setup is complete. Friday deep-dive session to be scheduled; coordination with Swapna ongoing. Centralized prompt Excel sheet planned; Azure DevOps used for blocker tracking. | SME Review/Input
02.10.2025 | Thursday | Day 6 Status (Gandhi Jayanthi) | Day 6 Status | Day 6 Status | Studied Site Reliability Engineering (SRE) agent concepts and explored Azure cloud workflows to deepen understanding of cloud infrastructure and operational efficiency. | SME Review/Input | SME Review/Input
03.10.2025 | Friday | 09:40–10:00 AM & 11:20–11:45 AM – Discussed project status with team. 11:30 PM – Chaitanya shared status; took leave due to health issue. Responded to IT and Joseph’s emails regarding software installation delay. Escalated installation policy issue to Joseph, Rathinavelu, and Ravi. Joined call with Joseph on using free Visual Studio via Azure remote access (VMs). Attempted setup on student version; installed Visual Studio on cloud remotely. Multiple attempts to create SRE agent failed due to location mismatch (free educational account). 06:30–06:40 PM – Call with Archana on cloud remote access challenges. 09:00–09:30 PM – Daily status call with Archana & Swapna; confirmed remote access resolved; started .NET backend and SQL work. | Worked on the Frontend features and made an excel report on the prompt instructions we used to build the app using Github's copilot. Engaged in team meeting on daily status call and showed the final progress of the frontend, now started in the backend for our project as we got the Visual studio community today. Had to research about SRE agent to use it for our project. | Discussed the updated codebase with team members to ensure alignment. Took sick leave starting at 11:30 AM. Joined the daily status call with SMEs to synchronize on key deliverables and ensure alignment on ongoing tasks. | Created and tested the SRE agent as part of infrastructure reliability efforts. Attended daily status calls with Archana and Swapna to align on progress and priorities. Confirmed resolution of remote access issues. Initiated backend development using .NET and SQL, and began integrating backend services with the SQL database. | Emphasized effective prompting for precise AI responses; referenced Microsoft training links. Suggested specific prompts with default elements and functionalities for Angular components/services. Recommended prompts for default implementations and code optimization (e.g., “review code and suggest improvements”). Advised targeted code review by introducing errors and outdated Angular versions; test Copilot against a checklist. Highlighted need for coding standards in MD file (e.g., no inline CSS) and deliberate error testing. Reiterated efficiency goal: reduce task time drastically using Copilot. Mentioned project timeline: demo by 13th; backend work to start immediately. | Stressed creating a customized technical review checklist for Copilot. Checklist should include specific version requirements (e.g., Angular 19, .NET 4.8.1) and multiple technologies. Copilot should identify issues and suggest fixes based on checklist. Highlighted account-specific standards and preferences (e.g., Chevron prefers .NET, avoids open-source libraries). Emphasized training Copilot for targeted findings, not generic answers. Reaffirmed importance of checklist for guiding relevant code reviews.
04.10.2025 | Saturday | Worked on backend skeleton development using GitHub Copilot and assisted teammate in connecting to an Azure VM for remote cloud deployment and Visual Studio Community installation. | Weekend | Weekend | Developed the backend skeleton leveraging GitHub Copilot for faster scaffolding. Successfully established a connection to an Azure Virtual Machine to enable remote cloud deployment. Also completed the installation of Visual Studio Community Edition to support development and debugging workflows. | Weekend | Weekend
05.10.2025 | Sunday | Created ASP.NET folder structure in Visual Studio Community; added SQL, API, stock, and inventory files; integrated Angular frontend with backend via APIs; scheduled functionality check on 06.10.25 | Weekend | Weekend | Continued development on the ASP.NET project backend, initiating integration of essential frontend components for functionality checks. Verified core features to ensure proper interaction between backend and frontend layers. | Weekend | Weekend
06.10.2025 | Monday | Integration & Performance Update: Issue: Delay in loading Angular frontend hosted on Azure Remote Cloud. Current Setup: Backend in Cloud Remote Visual Studio Community; Frontend in VS Code. Suggestion: Integrate both frontend and backend within Visual Studio Community to reduce connectivity issues. Calls & Discussions: 4:45 PM – 5:30 PM: Project status and blockers discussed with Ravi Sir. 6:30 PM – 6:45 PM: Progress and challenges discussed with SME Archana. Recommendations: Use Postman alongside Swagger and local builds for API testing. Host Angular frontend on Azure VM to improve performance. Deploy backend as Azure App Service with SQL Database for better scalability and reliability.Had connected with SMEs for progress and updates | Tested our Frontend app with a checklist and updated it to meet the code quality using the Github copilot. Documented all those prompts and checklists in an excel. We also did a good progress on the backend in the Visual studio community in the Azure Cloud. Engaged in the daily meet with SMEs and solved the issues that we had while working on the backend. | Conducted a comprehensive code review checklist for the frontend of the Inventory Management application. Utilized GitHub Copilot to assist in evaluating code quality and consistency across the application. Documented all required actions and improvements based on Copilot's suggestions, along with the corresponding verdicts. The findings have been consolidated for further implementation and tracking. | We made significant strides on the backend development, working extensively within Visual Studio Community hosted on Azure Cloud. Collaborating closely with SMEs during our daily syncs, we successfully resolved several backend-related issues, improving both performance and reliability. Meanwhile, the frontend was tested against a comprehensive checklist to ensure code quality, with enhancements guided by GitHub Copilot. All prompts and validation steps were documented in an Excel sheet for future reference and traceability. Would you like this formatted for a report, email, or project update document? | SME Review/Input | SME Review/Input
07.10.2025 | Tuesday | Connected with Ravi to update the project status. Worked on backend integration and API testing. Reviewed code and followed provided instructions. Referred to materials on code review standards for Angular and .NET 8 full-stack development. | Worked on the backend part, and researched about the the integration part for our project, explored the swagger api and tested it with basic setup of our project | Successfully set up the virtual machine environment for development. Verified code readiness and ensured the frontend was functional. Delivered a working demo by integrating an instruction file to guide standard-compliant development practices. | Utilized Postman, Swagger, and local builds to thoroughly test API endpoints and ensure consistent behavior across environments. and did some testing | SME Review/Input | SME Review/Input
08.10.2025 | Wednesday | Solved integration issues and worked on SSMS for local DB. Had connected with Ravi and Team for understanding Team Dynamics and all Team Personal interaction between Team and Ravi. Connected with SME for Progress updating and Blockers. | Tested the swagger api with the backend part of our project, which had some issues and we resolved it. Engaged in daily status call with our SMEs. | Explored the implementation of a pre-commit code review feature triggered via pull requests. Identified significant disruptions in the repository due to this approach. Decided to revert and instead focused on refining the code review checklist and designing prompt-based review guidelines to maintain code quality. | Applied final changes to both backend and frontend components of the project. Conducted thorough API testing using Postman, Swagger, and local builds to ensure consistent behavior across environments. | SME Review/Input | SME Review/Input
09.10.2025 | Thursday | Complete Fullstack was completed in Personal Laptop worked fine. And had a recording of the Project done for Full stack | we worked on our database for our project using SSMS server, which we connected with our backend part and tested the swagger api with our server part and it worked properly. Engaged in daily status call with our SMEs | Enhanced the frontend code review checklist by categorizing it into three distinct types tailored to different use cases. Conducted thorough code reviews using each checklist and generated detailed reports evaluating compliance with coding standards. Created a comprehensive demo presentation to showcase project progress and review methodology. | Finalized the project presentation (PPT) and conducted a pre-demo session with the Subject Matter Expert (SME) to showcase the complete functionality and gather feedback. | SME Review/Input | SME Review/Input
10.10.2025 | Friday | Had Call with SME on progress, Had lot of changes as inputs from SMEs and Showed partial demo of Full stack, sql DB and code review.Asked for fine tune. | We Tried integrated our backend and ssms server with our frontend part and tested every features in the front-end is reflecting in the backend or not. Engaged in daily status call with our SMEs. | Validated the end-to-end workflow to ensure error-free execution. Designed and finalized the architecture diagram for the project. Engaged with Subject Matter Experts (SMEs) to gather feedback and implemented their suggestions to improve the code review framework. | Incorporated feedback and suggestions from the review into the final presentation (PPT), ensuring clarity and alignment with project goals. | SME Review/Input | SME Review/Input
11.10.2025 | Saturday | Changed the UI and worked on complete full stack and end to end system and done with verificationa and validation. | Weekend | Initiated the development of an automated code review task to streamline the review process. | Weekend | Weekend | Weekend
12.10.2025 | Sunday | Purchased Github copilot pro version to test the full stack project we developed and data Deployed to SQL DB and testing the code review standards, organisation policies, testing checklisting, and generating report. | Weekend | Continued refining the coding standards checklist based on feedback and internal testing. | Weekend | Weekend | Weekend
13.10.2025 | Monday | Final minute touches and updates and upgrades from SMEs are implemented and brought to practice |  | Finalized the 3 frontend checklists and re-evaluated the codebase against each checklist. Generated updated reports and confirmed checklist effectiveness with SMEs, receiving validation for the approach.
14.10.2025 | Tuesday | PPT preparation, Rehearsals, demo practice within the team,Literature survey, future enhancements and conclusions were discussed and presented sucessfully. And received good feed back. |  | Conducted a comparative analysis of the project’s codebase using three advanced models: GPT-5, Claude Sonnet 3.5, and Gemini 2.5 Pro via GitHub Copilot. Evaluated each model’s performance in code review tasks and updated the final presentation with relevant metrics and insights.
Project Summary & Guidelines
Team Structure:
• Development: Vishnu Priya,Gokul, Sai Chaitanya, Dheeraj - Implementation
• SME Support: Archana & Swapna - Technical guidance and reviews
Daily Status Update Format:
• Current tasks completed
• Tasks planned for next day
• Any blockers or issues
Project Milestones to Track:
• Setup and initial analysis
• Knowledge fabric integration design
• Github Copilot enhancement implementation
• Testing and validation
• Documentation and deployment
Hours Distribution (Target: 80 hours total)
Total Working Days: 12
Average Hours per Day: 6.7 hours
Per Team Member Target: 20 hours each
Weekend slots reserved for any urgent requirements